REPUBLIC OF GHANA

BUDGET IMPLEMENTATION/ PERFORMANCE REPORT IN RESPECT

OF THE

NANUMBA NORTH MUNICIPAL ASSEMBLY

FOR THE

YEAR ENDING 31ST DECEMBER 2022

SUBMITTED TO MINISTRY OF FINANCE

IN

ACCORDANCE WITH

Sections 27, 30 (3) & 34 (1 & 2) of the Public Financial Management Act, 2016, Act 921

Table of Contents

PART A: PRINCIPAL ACCOUNT HOLDER’S (MCE) BRIEF	3

PART B: EXECUTIVE SUMMARY	4

POLICY OUTCOME INDICATORS AND TARGETS	9

PART C: STRATEGIC OVERVIEW OF THE MUNICIPALITY	11

VISION:	11

MISSION:	11

GOAL:	11

CORE FUNCTIONS:	11

POLICY OBJECTIVES	14

DISTRICT ECONOMY	14

Agriculture	14

Road Network	15

Energy	15

Health	15

Education	17

Market Centres	19

Water and Sanitation	19

Tourism	20

MONITORING AND EVALUATION MATRIX FOR PROGRAMME BASED BUDGET	21

PART D: KEY FINANCIAL PERFORMANCE BY PROGRAMME FOR THE PERIOD	36

PART E: SUMMARY OF EXPENDITURE BY ECONOMIC CLASSIFICATION	38

PART F: CASH POSITION	39

PART G (i): SUMMARY OF 2022 IGF PERFORMANCE BY REVENUE ITEMS FOR THE PERIOD	40

(II): EXPENDITURES ON 2022 IGFS BY ECONOMIC CLASSIFICATION	40

PART H: STAFF ESTABLISHMENT BY GRADE (GOG ONLY)	41

PART I: IGF STAFF BY NON-ESTABLISHED POST	44

PART J: ACTIONS TAKEN TO IMPLEMENT THE RECOMMENDATIONS OF PARLIAMENT IN RESPECT OF THE MOST RECENT REPORT OF THE AUDITOR-GENERAL IN ACCORDANCE WITH SECTION 27(4)(d) OF PFM Act	45

PART K: DETAILS OF ON-GOING PROJECTS	46

PART L: CONCLUSION	47

# PART A: PRINCIPAL ACCOUNT HOLDER’S (MCE) BRIEF

The 2022 Annual Budget Performance Report (ABPR) was presented to the General Assembly of the Nanumba North Municipal Assembly in accordance with section 27(1-4) of the Public Financial Management Act, 2016 (Act 921). This report assesses the implementation of the 2022 Composite Budget drawing inspiration from the Medium Term Development Plan (MTDP) and the National Development Policy Framework under the theme “Consolidating the Gains, for Growth, Jobs and Prosperity for All”.

Through the ABPR, Government at the sub-national level continues to fulfil its commitment to advance good economic governance, protect the public purse, ensure operational and managerial efficiency in the use of public resources. This report details and analyses the utilization of public resources by the Assembly, and summarises the status of implementation of key policy initiatives, programmes, and projects.

As you may be aware, 2022 was a challenging year by virtue of slow in central government transfers to the local authorities. The down surge in central government transfer is attributed to the economic shocks posed by the after mouth of the Russia-Ukraine War and the Corona Virus Disease (COVID-19) pandemic. However, through decisive leadership, the Municipal Assembly was able to manage and mitigate the impact by supporting livelihoods through compassionate, competent, and courageous leadership.

It is my hope that we use the feedback we got from this report to improve on our engagements with citizens and other relevant stakeholders on the economic governance of our dear municipality and the nation at large.

On behalf of Municipal Assembly, I take this opportunity to thank all those who contributed to the preparation of this Budget Performance Report, especially the Budget Committee.

God Bless us all.

# PART B: EXECUTIVE SUMMARY

This report represents the budget performance of the Nanumba North Municipal Assembly for the period 1st January to 31st December 2022 as required by Section 27 of the Public Financial Management Act, 2016 (Act 921). Accordingly, the 2022 Budget Performance Report represents the status of implementation of key policies, programmes, and projects undertaken by the Assembly.

The 2022 Budget focused on improving access to education and health care service whiles tackling bottlenecks in achieving food security in the municipality. This will support in consolidating the gains chalked within the previous years of successful budget implementation to achieve Government’s targets for growth and ensure jobs and prosperity for citizens.

Financial performance

The revenue performance of the Municipal Assembly for the 2022 fiscal year was 61.84% of the target. An amount of revenue that was realized as at the month ending 31st December, 2022. Total revenue amounted to GH¢ 7,793,972.36 with GoG transfers constituting 45.21%. Of the total GoG transfers to the municipality, GH¢ 3,494,173.31 meant for compensation payment (salaries and wages to staff on government-mechanized payroll) and GH¢ 29,440.37 is for goods and services transfers to departments. DACF for Assembly releases constituted 26.51% of the total revenue for 2022. An amount of GH¢ 1,162,183.92, constituting 14.91% of total revenue, was received in the form of DACF-RFG (formally known as DDF). Revenue generated within the municipality for the 2022 fiscal year amounted to GH¢ 423,594.85, constituting about 5.43% of the total actual revenue of the Assembly.

In terms of IGF, of the GH¢ 423,594.85 revenue mobilized within the fiscal year, the best source of the IGF came from fees and rent. These two revenue sources alone constituted about 71.81% of IGF. Licenses came third in term of performance raking in an amount of GH¢ 73,281.00. Poor performing revenue sources included lands, fines, basic rate and property rates. Strategies has been put in place to firm up existing approaches in mobilizing revenues from these poor performing sources.

Key Policy Outcome Indicators and Targets

Local resources mobilization is very critical in bring development to the citizenry. A policy outcome of measuring the performance of the Assembly in term of revenue mobilization has been set. These indicators include growth in IGF and percentage of IGF collected against the target. With improvement in IGF mobilization strategies, the Municipal Assembly was able to rake in 0.83% more than the projected IGF of GH¢ 420,122.00. However, there was a surge in IGF revenue collection in 2022 compared the 2023 fiscal year.

In terms of education, there has been an increase in BECE performance from 2019 to 2020. Percentage of students attaining aggregate 6-36 was 57.9%, 72.3% and 90.5% respectively for 2019, 2020 and 2021. Over the years, the boys continue to perform well than their counterpart. On improving hygiene and sanitation, the Assembly made tremendous improvement in number of ODF communities. There has been an increase by 46 communities declared ODF.

Expenditure by Economic Classification

The total expenditure of the Assembly totaled GH¢ 8,109,457.84. The expenditure performance of the municipality in terms of economic classification shows that an amount of GH¢ 1,877,298.35 was spent on the provision of infrastructural facilities (assets), GH¢ 2,648,181.18 was spent on goods and services and GH¢ 3,583,978.31 being expenditure on compensation of employees. Specifically on IGF, out of the total expenditure of GH¢ 390,957.20, GH¢ 89,805.00 was expensed for the payment of casual workers and other allowances whereas the remaining GH¢ 301,152.20 was spent on goods and services.

The Municipal Assembly’s Staff Strength: - The 2022 financial year recorded total staff strength of 170 with 137 of the staff on mechanized central government payroll and the remaining 33 staff being casual workers paid form the Assembly’s Internally Generated Fund (IGF). Some departments such as Works and Physical Planning still lack critical and technical staff to under technical duties in development control, spatial planning and engineering related activities.

Government Projects/Contracts:- The year 2022 turned out to be very challenging due to the persistence of the shocks from international economic crises resulted from the COVID-19 pandemic and the Unkraine-Russia war. This negatively affected central government transfers to the municipality to carry out planned activities. Amidst fighting the pandemic and ensuring a stable economy, Government executed a number of projects across the country in addition to the flagship programmes and other policy initiatives.

In all, eleven (11) infrastructure projects were implemented in the five broad sectors of the economy with an initial total budget of GH¢ 2,042,300.55. These projects did not witness various degrees of adjustments in their contract sums during the year. The contractors did their best to execute these projects within the ceilings despite general increases in construction cost. Cumulative payment reported as at end December 2022 amounted to GH¢ 1,295,691.65 (representing 63.44 per cent of the total amount budgeted for the projects) leaving an outstanding amount of GH¢ 746,608.90 for all projects.

Key Achievement in 2022: - Update on Government Flagship Programmes

The highlights of the Municipal Assembly’s successes in the implementation of the social intervention/flagship programmes in 2022 is presented as follows:

- Agriculture Modernization:– Various projects, such as Planting for Food and Jobs (PFJ), Planting for Export and Rural Development (PERD), Rearing for Food and Jobs (RFJ), Agriculture mechanization, benefitted from some support from the Municipal Assembly in terms of facilitation. Shared investment supports in the form of supply of improved seeds, and animal breeds, supply of fertilizer, warehouse rehabilitation, deployment and management of power tillers, tractors, and irrigation facilities, as well as provision of extension services have been critical.

- Industrilisation: – The one district one factory project that started in the municipality during the year 2020 have been completed, commissioned and has started operation. The agro processing factory, name Global Almass, processes cassava and yams into Fufu floor, Kunkunte, Gari, Capioca etc. The Assembly trained farmers and out growers on improved and required variety of cassava that can feed the factory. Access road to link the factory to the main Bimbilla-Chamba road. A transformer was also provided to ensure regular and sufficient power supply to the factory. The drive towards industrilisation has been boosted with the setting up of the African Continental Free Trade Area (AfCFTA) Secretariat in Ghana. The Strategic Anchor Industries Initiative, which is under the Industrial Transformation Agenda, enabled Government to grant special incentives to support local vehicle assembly. AfCFTA offers an opportunity for the products of Global Almas to have easy access to the regional market.

Sustainable Development Goals Allocation Report

Generally, dramatic performance was made in efforts to achieve SDG 2, 3 and 4 with little improvements on the rest of the SDGs. On quality education, some gains have been made in achieving SDG 4 that seeks to ensure inclusive and equitable quality education and promote lifelong learning opportunities for all. About 51.05% of the Assembly’s capital expenditure (GH¢ 958,382.25) was spent on the provision of educational infrastructure towards achieving the SDG 4.

Towards achieving SDG 3 that seeks to ensure healthy lives and promote the well-being for all at all ages, the Municipal Assembly committed barely 28.44% of its 2022 capital expenditure amounting to GH¢ 533,930.00 for the provision of heath infrastructure and supporting health care delivery programs. Key among these projects has been the construction of CHPs compounds, clinical and hospital equipment, nurses’ quarters, etc.

On achieving zero hunger (SDG 2), an amount of GH¢ 832,115.26 was spent in the provision of agriculture extention services through home and farm visits, establishment of demonstration sites and radio programs on the adoption of best agronomic practices. This is intended to end hunger, achieve food security and improved nutrition and promote sustainable agriculture.

Challenges and recommendations

In conclusion, the Municipal Assembly remains focused in the implementation of outlined policies and programmes to improve and safeguard livelihoods as well as the lives of the good people of the Municipality. These achievements reinforce the commitment of the Municipal Assembly to this cause with anticipation that rebuilding the economy in the ensuing years would be much quicker. Challenges that have hindered the achievement of the goals include the delay and inadequate release of central government statutory transfers such as DACF, DACF-RFG, GoG and other transfers. The following other challenges are apparent even though necessary strategies have been put in place but funds to execute them is hindering its success.

  - Chieftaincy conflict

  - Revenue under performance due to leakages and loopholes

  - Inadequate educational infrastructure

  - High prevalence of open defecation

  - Loss of trees and vegetative cover

  - Deplorable roads

  - Gaps in physical access to quality health care

  - Communal Land disputes

The Assembly intend to firm up strategies in internal revenue mobilize in order to harness local resources for development. In addition, central government should ensure the release of adequate financial resources per annual ceilings and on time for timely execution of development projects and programs in the municipality.

## POLICY OUTCOME INDICATORS AND TARGETS

| Outcome Indicator Description | Unit of Measurement | Base Line |  | Target for the Year 2022 |  | Latest Status |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Annual | Value | Annual | Value | Annual | Value |  |
| Improve financial management | % growth in IGF | 2021 | 7.2% | 2022 | -5.2% | 2023 | 10% |  |
|  | % IGF performance mobilized | 2021 | 122.49% | 2022 | 100.83% | 2023 | 100% |  |
|  | % of expenditure kept within budget | 2021 | 100 | 2022 | 100 | 2023 | 100% |  |
| Teaching and learning improved in the municipality | Percentage of male students qualifying for SHS (Aggregate 36 and below) | 2021 | 91.2% | 2022 | Waiting analysis | 2023 | 100% | The 2022 analysis of the BECE results is not done yet |
|  | Percentage of female students qualifying for SHS (Aggregate 36 and below) | 2021 | 89.7% | 2022 | Waiting analysis | 2023 | 100% | The 2022 analysis of the BECE results is not done yet |
|  | No. of schools with standard structures (permanent structures) | 2021 | 72 | 2022 | 75 | 2023 | 82 |  |
| Sub-district structures operationalized | No. of area councils getting 50% of revenue ceded to them | 2021 | 0 | 2022 | 0 | 2023 | 6 |  |
|  | No. of area councils with renovated and furnished offices | 2021 | 0 | 2022 | 0 | 2023 | 6 |  |
| Peace and security improved | No. of murder cases recorded | 2021 | 1 | 2022 | 7 | 2023 | 0 |  |
|  | No. of residents possessing illegal firearms | 2021 | 2 | 2022 | 0 | 2023 | 0 |  |
|  | No. of robbery cases recorded | 2021 | 1 | 2022 | 1 | 2023 | 0 |  |
|  | Curfew hours on Bimbilla | 2021 | 9 | 2022 | 12 | 2023 | 4 |  |
| Hygiene and sanitation of the district improved through CLTS | Accumulated number of communities declared ODF | 2021 | 24 | 2022 | 70 | 2023 | 100 |  |
| Policy formulation, implementation and monitoring through the legislature of the Assembly enhanced | No. of signed minutes of Assembly meetings held | 2021 | 3 | 2022 | 3 | 2023 | 3 |  |
| Citizen participation in planning and budgeting increased | No. of signed minutes for executive and sub-committees | 2021 | 3 | 2022 | 3 | 2023 | 3 |  |
|  | No. of town hall meeting held with signed minutes | 2021 | 20 | 2022 | 23 | 2023 | 25 |  |
| Water facilities in the district increased | No. of boreholes rehabilitated | 2021 | 10 | 2022 | 16 | 2023 | 17 |  |
|  | No. of dugouts rehabilitated | 2021 | 3 | 2022 | 6 | 2023 | 7 |  |
| Food security improved | No. of farmers (especially women) trained on food safety and preservation | 2021 | 93 | 2022 | 150 | 2023 | 300 |  |
|  | No. of vulnerable households receiving small ruminants | 2021 | 150 | 2022 | 300 | 2023 | 300 |  |
|  | No. of households helped with ploughing and supply of seeds | 2021 | 500 | 2022 | 500 | 2023 | 500 |  |

# PART C: STRATEGIC OVERVIEW OF THE MUNICIPALITY

## VISION:

The Nanumba North Municipal Assembly envisages a peaceful, progressive and well-developed Municipality with high standard of living for its people in its area of jurisdiction in a conducive atmosphere, where the dreams and aspirations of its inhabitants can be attained and maximized.

## MISSION:

The Nanumba North Municipal Assembly exists to facilitate an improvement in the quality of life of the people by harnessing resources and collaborating with private and public agencies for the provision of facilities and the delivery of quality services.

## GOAL:

The broad development goal of the Nanumba North Municipal Assembly is to bridge the poverty gaps of all facets of the society and ensure accelerated socio-economic development of the Municipality. Specifically, the Municipal Assembly seeks to achieve the following.

- Build a Prosperous Society;

- Create Equal opportunities for all;

- Safeguard the natural environment and ensure a resilient built environment; and

- Maintain a stable, united and safe society.

## CORE FUNCTIONS:

- Subject to the Local Governance Act - 2016 (ACT 936), the Nanumba North Municipal Assembly;

- Exercises political and administrative authority in the Municipality;

  - Promotes local economic development;

  - Provides guidance, gives direction to and supervises other administrative authorities in the Municipality as may be prescribed by law.

- The Nanumba North Municipal Assembly exercises deliberative, legislative and executive functions.

- Without limiting subsections (1) and (2), The Nanumba North Municipal Assembly;

  - is responsible for the overall development of the Municipality;

  - Formulates and execute plans, programmes and strategies for the effective mobilization of the resources necessary for the overall development of the Municipality;

  - Promotes and supports productive activity and social development in the Municipality and removes any obstacles to initiative and development;

  - Sponsors the education of students from the Municipality to fill particular manpower needs of the Municipality especially in the social sectors of education and health, making sure that the sponsorship is fairly and equitably balanced between male and female students;

  - Initiates programmes for the development of basic infrastructure and provide Municipal works and services;

  - is responsible for the development, improvement and management of human settlements and the environment;

  - in co-operation with the appropriate national and local security agencies, be responsible for the maintenance of security and public safety;

  - Ensures ready access to courts in the Municipality for the promotion of justice;

  - act to preserve and promote the cultural heritage within the Municipality;

  - Initiates, sponsor or carry out studies that may be necessary for the discharge of any of the duties conferred by this Act or any other enactment; and

  - Performs any other functions that may be provided under another enactment.

- The Nanumba North Municipal Assembly shall take steps and measures that are necessary and expedient to:-

  - Executes approved development plans for the Municipality;

  - Guides, encourage and support sub-Municipal local structures, public agencies and local communities to perform their functions in the execution of approved development plans;

  - Initiates and encourages joint participation with other persons or bodies to execute approved development plans;

  - Promotes or encourage other persons or bodies to undertake projects under approved development plans; and

  - Monitors the execution of projects under approved development plans and assess and evaluate their impact on the development of the Municipality and national economy in accordance with government policy.

- The Nanumba North Municipal Assembly co-ordinates, integrates and harmonizes the execution of programmes and projects under approved development plans for the Municipality and other development programmes promoted or carried out by Ministries, Departments, public corporations and other statutory bodies and non-governmental organizations in the Municipality.

- The Nanumba North Municipal Assembly in the discharge of its duties

  - is subject to the general guidance and direction of the President on matters of national policy; and

  - Acts in co-operation with the appropriate public corporation, statutory body or non-governmental organization.

- Public corporations, statutory bodies and non-governmental organizations shall co-operate with a Municipal Assembly in the performance of their functions.

- In the event of a conflict between a Municipal Assembly and an agency of the central Government, public corporation, statutory body, non-governmental organization or individual over the application of subsection (5), (6) or (7), the matter shall be referred by either or both parties to the Northern Regional Coordinating Council for resolution.

- The Instrument that establishes a particular Municipal Assembly or any other Instrument may confer additional functions on the Municipal Assembly.

## POLICY OBJECTIVES

The following Policy Objectives have been adopted from the National Medium-Term Development Policy Framework (NMTDPF) for implementation in 2023:

- Enhance inclusive and equitable access to, and participation in quality education at all levels.

- Ensure affordable, equitable, easily accessible and Universal Health Coverage (UHC).

- Ensure the reduction of new HIV and AIDS/STIs infections, especially among the vulnerable groups.

- Mobilise additional financial resources for development.

- Significantly reduce all forms of violence & related death rates everywhere.

- Improve access to safe and reliable water supply services for all.

- Increase number of youth and adults with relevant skills.

- Enhance access to improved and reliable environmental sanitation services.

Strengthen social protection, especially for children, women, persons with disability and the elderly.

## DISTRICT ECONOMY

Nanumba North Municipal Assembly with Bimbilla as the capital is an agrarian economy with Yam production and trade being the occupation of majority of the population. Bimbilla is one of the famous towns along the Eastern Corridor Road with immense commerce largely agribusiness business as the preoccupation of the municipality.

### Agriculture

The Agriculture sector (forestry and fishing) employs majority of the residents. About 79.4% of the total work force is into Agriculture which basically makes the Municipal economy agrarian. Major Crops cultivated in the Municipality include yam, maize, soya beans. Animal husbandry is also predominant among the people.

The next leading sector is wholesale and retail (7.6%), which may largely be the effect of the closeness of the Municipality to the eastern border of the country, which makes it a market for secondary imported goods. Manufacturing, accommodation and food services and education also employ reasonable number of people relative to the already mentioned industries.

Out of the total land area of 173,459 hectares, about 130,094 hectares representing 75% are agricultural lands. However, only 46,566 hectares representing 28% is under cultivation. There is currently no area under irrigation despite the fact that two major rivers – Oti and Dakar run through the Municipality. It also has numerous productive valleys: the Kaleogu, Sabonjida. Juo, Jua and Salnayili for commercial rice production, but all these are underutilized. Crops grown are roots and tubers, cereals, legumes and tree crops such as teak and cashew nuts. Animal rearing including poultry keeping is an integral part of every household.

### Road Network

The Municipality has a total road network of 601 kilometers. This is made up of 73 kilometers of trunk roads radiating from the Municipal capital, Bimbilla has 292 kilometers of engineered feeder roads, 128 kilometers of un-engineered feeder roads which are usually farm tracks, 19.31 kilometers of partially engineered roads. None of these roads is tarred. The trunk roads though motorable throughout the year are difficult to ply during the rainy season. The partially engineered and the non-engineered link the communities to the hinterland. However, they are only motorable during the dry season.

### Energy

A total number of 103 communities out of the 203 number are not connected to the national grid. The current access to electricity can impact negatively on investment particularly those into agro processing sub sector. The use of gas for cooking is also very low with no LPG service point in the Municipality.

### Health

The Municipality has only one Hospital, 13 CHPs, 5 Health Centres, and 2 Clinics as well as a Private Clinic. Only one medical doctor delivers health services to the people of the Municipality. This presents a Patient Doctor Ratio of 1:70792. The relevant staffing information and staff requirement that man the health facilities is shown in Table 1.

Table 1: Staff Strength and the Categories

| Category of Staff | No. at Post | No. at Post MHD | No. Required | Deficit |
| --- | --- | --- | --- | --- |
| Medical Doctor | 2 | 2 | 3 | 1 |
| Physician Assistant (M A) | 7 | 2 (1 CHAG) | 11 | 4 |
| Anesthetists | 1 | 0 | 3 | 2 |
| Midwives | 26(2 on study leave) | 16(4 CHAG) | 100 | 74 |
| General Nurses | 71( 8 on study leave) | 37(4 CHAG) | 75 | 4 |
| Community Health Nurses | 53(9 on study leave) | 51(9 on study leave) | 78 | 25 |
| Field Technicians | 1 | 1 | 8 | 7 |
| Enrolled Nurses | 89 (6 on study leave) | 37 (6 CHAG) | 140 | 51 |
| TOTAL | 248 | 144 | 415 | 167 |

Diseases such as Malaria, URTI, Diarrhea, UTI, Anaemia, and Pneumonia continue to be the main diseases as cases received at various health centers, clinics and hospital in the municipality. Table 2 represents the list of cases of key diseases.

Table 2: Prevalence of Diseases in the Municipality

| Disease | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cases | % | Cases | % | Cases | % | Cases | % | Cases | % |
| Malaria | 7,486 | 25.9 | 16,034 | 23 | 22,188 | 27 | 25,704 | 27 | 16,647 | 30 |
| URTI | 4,212 | 14.6 | 7,342 | 11 | 4,002 | 5 | 8,359 | 9 | 5,289 | 9 |
| Diarrhea Diseases | 3,564 | 12.3 | 5,651 | 8 | 4,756 | 6 | 3,738 | 4 | 2,292 | 4 |
| UTI | 1,568 | 5.4 | 4,736 | 7 | 5,999 | 7 | 5,564 | 6 | 3,957 | 7 |
| Rheumatism & Other Joint Pains | 1,524 | 5.3 | 2,568 | 4 | 1,133 | 1.4 | 1,930 | 2 | 1,709 | 3 |
| Pneumonia | 1,131 | 3.9 | 6,072 | 9.3 | 1,415 | 1.7 | 2,475 | 3 | 955 | 2 |
| Typhoid Fever | 810 | 2.8 | 2,530 | 4 | 921 | 1 | 1,094 | 1 | 670 | 1 |
| Anaemia | 746 | 2.6 | 777 | 2.9 | 4,059 | 5 |  |  |  |  |
| Hypertension | 538 | 1.9 | 1,165 | 4.3 | N/A | N/A |  |  |  |  |
| Skin Diseases | 463 | 1.6 | 683 | 2.5 | 1,000 | 1.2 |  |  |  |  |
| Ulcer | N/A | N/A | N/A | N/A | 2,885 | 3.6 |  |  |  |  |
| Intestinal Worm | N/A | N/A | N/A | N/A | 1,764 | 2.2 |  |  |  |  |

Public health diseases concern children under five years: Meningitis; measles; AFP (Polio): Yellow Fever; Leprosy: Guinea worm; antigen dropout rates; BCG/MR1 dropout rates.

Table 3: Public Health Diseases

| Disease | 2019 |  | 2020 |  | 2021 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Suspect | Confirm | Suspect | Confirm | Suspect | Confirm |
| Meningitis | 8 | 3 | 5 | 1 | 1 | 0 |
| Measles | 2 | 0 | 1 | 0 | 2 | 0 |
| Yellow Fever | 3 | 0 | 2 | 0 | 3 | 0 |
| Cholera | 0 | 0 | 0 | 0 | 0 | 0 |
| Viral Hemorrhagic Fever/Ebola | 0 | 0 | 0 | 0 | 0 | 0 |

Note: For all age group (under five years and above)

The only one meningitis case confirmed in 2021 was treated and discharged. There have been no case of cholera, Viral Hemorrhagic Fever/Ebola, Yellow fever and Measles recorded from 2016 to date in the Municipality.

Very important to note is how the Municipality has performed in terms of Antenatal coverage, Family Planning Acceptor Rate, Total Number of Maternal Deaths, Moderately Underweight Children under five years receiving at least one dose of vitamin A supplementation, and Children under five years measure for stunting. Data on this information is also presented in Table 4.

Table 4: Key Performance indicators from 2016 to 2021

| Indicator | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |
| --- | --- | --- | --- | --- | --- | --- |
| Antenatal coverage | 106.6 | 100 | 87.9 | 94.9 | 101.1 | 86.5 |
| Family Planning Acceptor Rate | 23 | 22.4 | 21.9 | 30.4 | 26.3 | 10 |
| Total Number of Maternal Deaths | 5 | 6 | 1 | 3 | 1 | 0 |
| Moderately Underweight | 3.5 | 3.5 | 0.67 | 1.7 | 0.06 | 0.14 |
| Children under five years receiving at least one dose of vitamin A supplementation | 60.5 | 180.4 | 139.5 | 85.3 | 143.6 | 120.9 |
| Children under five years measure for stunting | 0 | 0 | 0 | 8.9 | 26.1 | 43.6 |

### Education

The Municipality has a total of 242 educational institutions at the pre-tertiary level. This is made up of 92 pre-schools of which 83 are public, 129 Primary Schools with 100 being public schools, 38 Junior High Schools with 7 being private and 2 Senior High Schools of which one is public and the other is private. The Municipality also has one College of Education. The Municipality has 901 teachers with 582 being trained and 319 untrained. Table 5 represents statistics on the number of schools across the municipality from creche to Senior High School level.

The Municipality can boast of 172 Basic Schools (140 public and 32 Private), two (2) Senior High Schools (1 public and 1 private) and one public College of Education.

Number of Schools in the Municipality by Level

| Level of School | Academic Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019 |  |  | 2020 |  |  | 2021 |  |  |
|  | Public | Private | Total | Public | Private | Total | Public | Private | Total |
| Kindergarten | 99 | 26 | 125 | 100 | 26 | 126 | 100 | 27 | 127 |
| Primary | 100 | 28 | 128 | 100 | 28 | 128 | 100 | 29 | 129 |
| Junior High School | 39 | 12 | 51 | 39 | 12 | 51 | 40 | 12 | 52 |
| Senior High School | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 2 |

Table 5: Number of schools and teachers

| Indicator |  | 2019/2020 |  |  | 2020/2021 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Public | Private | Total | Public | Private | Total |
| No. of Schools | Creche | 0 | 13 | 13 | 0 | 17 | 17 |
|  | KG | 99 | 26 | 125 | 100 | 33 | 133 |
|  | PRIM | 100 | 28 | 128 | 100 | 34 | 134 |
|  | JHS | 39 | 12 | 51 | 39 | 12 | 51 |
|  | SHS | 1 | 1 | 2 | 1 | 1 | 2 |
| No. of Teachers | Creche |  | 29 | 29 |  | 45 | 45 |
|  | KG | 237 | 51 | 288 | 184 | 58 | 242 |
|  | PRIM | 791 | 119 | 910 | 603 | 134 | 737 |
|  | JHS | 549 | 60 | 609 | 392 | 61 | 453 |
|  | SHS | 85 | 19 | 104 | 100 | 19 | 119 |

Number of Permanent/standard classrooms and Pupil Classroom Ratio (PCR)

| Level | Academic year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2020 |  |  | 2021 |  |  | 2022 |  |  |
|  | Total enrol. | No. of class- rooms | PCR | Total enrol. | No. of class- rooms | PCR | Total enrol. | No. of class- rooms | PCR |
| KG | 10740 | 110 | 98 | 10287 | 116 | 89 | 9728 | 122 | 80 |
| Primary | 25725 | 450 | 57 | 26112 | 444 | 59 | 23198 | 442 | 52 |
| JHS | 6993 | 152 | 46 | 6457 | 182 | 35 | 5247 | 188 | 28 |
| SHS | 1920 | 37 | 52 | 1616 | 37 | 44 | 1179 | 37 | 32 |

Trend in the BECE pass rate presented in Table 6 indicate that the Municipality made tremendous performance in terms of the past rate from the 2019 to 2020 Basic Education Certificate Examination. The Municipality emerged from as low as an overall performance of 8.05% of students sitting in for the exams to as high as 72.3%.

Table 6: BECE Pass Rate from 2016 to 2020

| Year | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |
| --- | --- | --- | --- | --- | --- | --- |
| Boys | 9.9 | 41.82 | 38.61 | 59.5 | 75.5 | 91.2 |
| Girls | 5.39 | 33.44 | 38.61 | 56 | 68.2 | 89.7 |
| Total | 8.05 | 38.25 | 38.61 | 57.9 | 72.3 | 90.5 |

The municipality experienced excellent performance in BECE pass rate in 2021. Overall, about 90.5% of the student who sat for the BECE exams got aggregate 6 to 36. However, the WASSCE performance for 2021 is very poor with an overall performance of 8.67%. In both BECE and WASSCE, boys performed more than their female counterparts.

BECE Proficiency by Core Subjects

| Year | % Subject Proficiency (Grade 1 - 6) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | English |  | Maths |  | Science |  | Social Studies |  |
|  | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls |
| 2019 | 67.2 | 61.2 | 82.4 | 80.5 | 78.1 | 75.3 | 91.4 | 89.7 |
| 2020 | 76.9 | 68.7 | 93.2 | 90.0 | 88.8 | 83.2 | 89.1 | 87.6 |
| 2021 | 53.5 | 55.6 | 80.8 | 80.3 | 58.6 | 60.9 | 67.2 | 66.9 |

Overall WASSCE Performance

| Year | No. that wrote exams |  |  | No. Passed (A1-C6) |  |  | % Passed |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Boys | Girls | Total | Boys | Girls | Total | Boys | Girls | Total |
| 2019 | 247 | 165 | 412 | 71 | 29 | 100 | 28.74 | 17.57 | 24.27 |
| 2020 | 331 | 301 | 632 | 50 | 20 | 70 | 15.11 | 6.64 | 11.07 |
| 2021 | 408 | 261 | 669 | 39 | 19 | 58 | 9.55 | 7.28 | 8.67 |

### Market Centres

The next leading sector is wholesale and retail (7.6%), which may largely be the effect of the closeness of the Municipality to the eastern border of the country, which makes it a market for secondary imported goods. As a result of the agrarian nature of the economy the market largely engages in the sales of farm produce such as Yam, Maize, Cowpea, Groundnuts etc. Commerce booms more in Bimbilla than the other market centers such as Chamaba, Lepusi, Bincharatanga, Lanja and Bakpaba.

### Water and Sanitation

A total of 103826 of the population have access to potable water. Potable water coverage in the Municipality now stands at 77.6% (CWSA, 2012). About 80 (Eighty) communities do not have access to any source of safe drinking water. Currently the Nanumba North Municipality depends only on one conventional treatment plant system which serve a section of Bimbilla town and Dangbenayili, 239 functioning boreholes, 3 hand-dug wells which dry up in the dry season, 20 dams/dugouts and streams.

There are 20 public toilets in the Municipality. Household latrines are mostly found in government premises and some smaller communities. Majority of the people in the Municipality practice the free-range system as a method of excreta disposal. About 79.4% of the communities practice this method.

### Tourism

There are notable tourist sites which includes the praying grounds at Kpalga, the grave of Gmantambu at Duuni, the xylophone at Glisiya.

## MONITORING AND EVALUATION MATRIX FOR PROGRAMME BASED BUDGET

Budget Programme Title: Management and Administration

| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator | Baseline (2021) Actuals | 2022 |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Budget Year Target | Annual Actual | Variance |  |
| National Objective: - Develop effective acceptable & transparent institution at all levels - Strengthen national institution to prevent violence, terrorism and crime - Ensure resp., inclusion, participatory and representative decision-making - Improve decentralized planning - Mobilize additional financial resources for development - Improve human capital development and management - Enhance capacity for high-quality, timely and reliable data |  |  |  |  |  |  |  |  |
| Programme Objective: - To provide institutional, administrative, human resource and financial support for the management of the Municipality - To effectively coordinate the various activities in the municipality including implementation of policies, programmes and projects. |  |  |  |  |  |  |  |  |
| Sub Programme Objective: - To co-ordinate the activities of various departments within the municipality - To provide administrative support to all departments and units within the assembly and ensure effective service delivery - To facilitate the provision of logistics for the various units and departments of the assembly |  |  |  |  |  |  |  |  |
| General Administration | Outcome 1: Enhanced Administrative Management of the Assembly |  |  |  |  |  |  |  |
|  | Output 1.1 | Regular Management meetings Held | No. of management meetings held | 12 | 24 | 5 | 19 | Only 5 management meetings were held |
|  | Output 1.2 | Meetings Entity Tender Committee Held | No. of Entity Tender Committee meetings held | 3 | 4 | 4 | 0 |  |
|  | Output 1.3 | Municipal Security Committee Meetings Organized | No. of MUSEC meetings held | 16 | 12 | 11 | 1 |  |
| Sub Programme Objective: - Improve financial management and reporting through the promotion of efficient Accounting system. - Ensure effective and efficient mobilization of resources and its utilization. |  |  |  |  |  |  |  |  |
| Finance and Audit | Outcome 2: Improved financial management |  |  |  |  |  |  |  |
|  | Output 2.1 | Revenue properly receipted and accounted for | Percentage increase in IGF | 6.05 | 5 | -5.20 | 10.2 |  |
|  | Output 2.2 | Revenue collection monitored and supervised | No. of visits to market Centre | 26 | 30 | 21 | (9) |  |
|  | Output 2.3 | Level of Implementation of Revenue Improvement Action Plan (RIAP) improved | % of Implementation of the RIAP | 100 | 100 | 65 | (35) |  |
|  | Output 2.4 | Monthly Financial reports prepared | No. of monthly financial reports prepared and submitted by 15th of every ensuing month | 9 | 9 | 9 | 0 |  |
| Sub Program Objective: - To manage the human resource of the Municipality Assembly efficiently and effectively so that a more motivated, team building and goal-oriented staff with up-to-date knowledge in their chosen fields are readily available for the execution of programmes and projects. |  |  |  |  |  |  |  |  |
| Human Resource Management | Outcome 3: Human resource management improved |  |  |  |  |  |  |  |
|  | Output 3.1 | Accurate and comprehensive HRMI data updated and submitted to RCC | No. of updates and submissions done | 9 | 12 | 9 | 3 |  |
|  | Output 3.2 | Staff assisted in performance appraisal | No. of staff appraised | 43 | 115 | 58 | 57 |  |
|  | Output 3.3 | Staff capacity built | No. of staff trained /supported for short courses | 78 | 124 | 36 | 88 |  |
| Sub Program Objective: - To establish a comprehensive, integrated, accurate and timely Plans and Budget that support policy formulation. - To ensure monitoring and evaluation of projects and programmes - Collect, compile, analyse, publish and disseminate demographic, health and economic data on the municipality. |  |  |  |  |  |  |  |  |
| Planning, Budgeting, Coordination and Statistics | Outcome 4: Decentralized planning and budgeting improved |  |  |  |  |  |  |  |
|  | Output 4.1 | Fee fixing resolution prepared | Fee fixing resolution prepared and gazetted by | 24th Jan. | 31st Dec. | 24th Jan. |  |  |
|  | Output 4.2 | Monitoring of projects and programmes | No. of site visits undertaken | 11 | 20 | 16 | (4) |  |
|  | Output 4.3 | Plans and Budgets produced and reviewed | Annual Action Plan prepared by | August | June | August |  |  |
|  |  |  | District Composite Budget prepared by | 29th Oct. | 31st Oct | 27th Oct. |  |  |
|  |  |  | AAP and composite budget reviewed by | 23rd August | 30th June | 21st August |  |  |
|  | Output 4.4 | Increased citizens participation in planning, budgeting and implementation | No. of public hearings organized | 1 | 2 | 1 | 1 |  |
|  |  |  | No. of Town-Hall meetings organized | 1 | 2 | 1 | 1 |  |
|  |  |  | Community Action Plans prepared | - | 50 | 36 | 14 |  |
|  | Output 4.5 | MPCU meetings held | No. of Meetings held with signed minutes | 2 | 4 | 4 | 0 |  |
|  | Output 4.6 | Budget Committee meetings held | No. of Meetings with signed minutes | 3 | 4 | 4 | 0 |  |
|  | Output 4.7 | Quarterly market readings conducted | No. of market reading conducted | 2 | 4 | 1 | 3 |  |
|  | Output 4.8 | Enumeration on demographic, health, education and economic data conducted | No. of enumerations undertaken | 0 | 3 | 0 | (3) |  |
| Sub Program Objective: - To ensure full implementation of the political, administrative and fiscal decentralization reforms |  |  |  |  |  |  |  |  |
| Legislative Oversights | Outcome 5: Citizens participation in decision making improved |  |  |  |  |  |  |  |
|  | Output 5.1 | Meetings of the General Assembly organized | No. of meetings held with signed minutes | 3 | 3 | 2 | (1) |  |
|  | Output 5.2 | Meetings of the Executive Committee and sub-committee organized | No. of Executive and Sub-committee meetings held with signed minutes | 22 | 24 | 12 | (12) |  |
|  | Output 5.3 | Capacities of Zonal Councils built | Number of training workshop | 2 | 2 | 1 | (1) |  |
|  |  |  | Number of zonal councils supplied with furniture | 2 | 2 | 1 | (1) |  |

Budget Programme Title: Social Service Delivery

| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator |  | Baseline (2021) Actuals | 2022 |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Budget Year Target | Annual Actual | Variance |  |
| National Objective: Enhance inclusive and equitable access to, and participation in quality education at all levels |  |  |  |  |  |  |  |  |  |
| Programme Objective: - To provide equal access to quality basic education to all children of school-going age at all levels - To improve access to health service delivery - Promote social development, facilitate in integrating the disadvantaged, vulnerable, and excluded in mainstream of development. |  |  |  |  |  |  |  |  |  |
| Sub Programme Objective: - To ensure inclusive and equitable access to education at all levels. - Provide relevant quality pre-tertiary education to all children. - To ensure an effective and efficient library services. |  |  |  |  |  |  |  |  |  |
| Education, Youth and Sports Services | Outcome 1: Standard of Education improved |  |  |  |  |  |  |  |  |
|  | Output 1.1 | Enrolment increased | Gross enrolment Rate (%) | KG | 69.8 | 95 | 93.1 | (1.9) |  |
|  |  |  |  | Primary | 71.5 | 95 | 91.2 | (3.8) |  |
|  |  |  |  | JHS | 48.6 | 70 | 62.9 | (71) |  |
|  |  |  |  | SHS | 12.4 | 30 | 17.3 | (12.7) |  |
|  |  |  | Gender Parity Index | KG | 0.92 | 1 | 0.96 | (0.4) |  |
|  |  |  |  | Primary | 0.94 | 1 | 0.94 | (0.6) |  |
|  |  |  |  | JHS | 0.93 | 1 | 0.98 | (0.2) |  |
|  |  |  |  | SHS | 0.80 | 1 | 0.86 | (0.14) |  |
|  | Output 1.2 | Literacy and Numeracy levels improved | BECE pass rate (%) | Total | 90.5 | 80 | - | - |  |
|  |  |  |  | Girls | 89.7 | 75 | - | - |  |
|  |  |  |  | Boys | 91.2 | 75 | - | - |  |
|  |  |  | Percentage of students with reading ability |  | 67 | 70 | 66 | (4) |  |
|  | Output 1.3 | Schools monitored | Percentage of schools visited for inspection |  | 23 | 90 | 78 | (12) |  |
|  | Output 1.4 | Organized quarterly DEOC meetings | No. of meetings organized |  | 3 | 4 | 2 | (2) |  |
|  | Output 1.5 | Brilliant but needy students supported | Number of students supported |  | 62 | 100 | 34 | (66) |  |
|  | Output 1.6 | Educational infrastructure provided | No. of classroom block with ancillaries constructed |  | 3 | 2 | 4 | 2 |  |
| Sub Programme Objective: - To achieve a healthy population that can contribute to socio-economic development of the Municipality and Ghana as a whole. |  |  |  |  |  |  |  |  |  |
| Public Health Services and Management | Outcome 2: Health care service delivery improved |  |  |  |  |  |  |  |  |
|  | Output 2.1 | Access to health service delivery improved | No. of CHPs compounds constructed |  | 0 | 2 | 2 | 0 |  |
|  |  |  | No. of Nurses Quarters constructed |  | 1 | 0 | 0 | 0 |  |
|  |  |  | No. of CHPs Compounds/Nurses Quarters renovated |  | 2 | 1 | 1 | 0 |  |
|  | Output 2.2 | Maternal and child health improved | No. of community durbars on ANC, safe deliver, PNC and care of new born and mother |  | 147 | 120 | 135 | 15 |  |
|  |  |  | % of staff trained on ANC, PNC & new-born care |  | 74% | 70% | 78% | 8% |  |
|  | Output 2.3 | HIV/AIDS infection reduced | No. of reported cases of HIV/AIDS |  | 28 | 5 | 33 | (28) |  |
| Sub Programme Objective: - Empower communities to shape their future by the utilisation of their skills and resources to improve their standard of living. - To integrate the vulnerable, Persons with Disability, the excluded and the Disadvantaged into the mainstream of society, protect and promote the right of children against harm and abuse. - To achieve the overall social, economic and cultural re-integration of older persons to enable them to participate in national development in security and dignity |  |  |  |  |  |  |  |  |  |
| Social Welfare and Community Development | Outcome 3: Enhanced child rights promotion and protection |  |  |  |  |  |  |  |  |
|  | Output 1.1 | Reduced incidence of domestic Violence, child protection, rural-urban migration, child labour | No. of communities sensitized |  | 17 | 20 | 20 | 0 |  |
|  | Output 1.2 | Childhood activities monitored | No. of childhood development centres monitored |  | 3 | 10 | 10 | 0 |  |
|  | Output 1.3 | Attendants in day care trained on psychology of children | No. of day care centres trained |  | 0 | 4 | 3 | -1 |  |
|  | Outcome 4: Enhanced wellbeing of the vulnerable |  |  |  |  |  |  |  |  |
|  | Output 1.1 | Vulnerable persons especially women in the community supported | No. of women groups supported in income generation ventures |  | 34 | 30 | 31 | 1 |  |
|  | Output 1.2 | PWDs supported financially | No. of PWDs supported financially |  | 154 | 100 | 51 | (49) |  |
|  | Output 1.3 | Reduced in-take of non - iodated salt | No. of women sensitized |  | 0 | 30 | 31 | 1 |  |
|  | Output 1.4 | Communities sensitized on good living | No. of communities sensitized |  | 5 | 20 | 18 | (2) |  |
| Sub Programme Objective: - To improve awareness of environmental sanitation and health issues through sensitization programmes. |  |  |  |  |  |  |  |  |  |
| Environmental Health and Sanitation Services | Outcome 5: Hygiene and sanitation improved |  |  |  |  |  |  |  |  |
|  | Output 1.1 | Communities triggered on CLTS | No. of communities triggered |  | 11 | 10 | 0 | (10) |  |
|  | Output 1.2 | Solid waste managed | No. of refused dumps evacuated |  | 9 | 3 | 0 | (3) |  |
|  | Output 1.3 | Improved Sanitation | No. of communities declared ODF basic |  | 3 | 15 | 0 | (15) |  |
|  |  |  | No. of communities declared ODF proper |  | 116 | 15 | 0 | (15) |  |
|  |  |  | No. of sanitary offenders prosecuted |  | 0 | 0 | 0 | 0 |  |
|  | Output 1.4 | Food venders medically screened and licensed | No. of venders screened and licensed |  | 316 | 500 | 155 | (345) |  |

Budget Programme Title: Infrastructure Delivery and Management

| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator | Baseline (2021) Actuals | 2022 |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Budget Year Target | Annual Actual | Variance |  |
| National Objective: - Enhance inclusive urbanization and capacity for settlement planning - Develop equal, reliable, sustainable and resilient infrastructure - Ensure universal access to affordable, reliable and modern energy services - Achieve universal and equitable access to water - Improve efficiency and effectiveness of road transportation infrastructure and services |  |  |  |  |  |  |  |  |
| Programme Objective: - To exercise district-wide responsibility in planning, management and promotion of harmonious, sustainable and cost-effective development of human settlements in accordance with sound environmental and planning principles. - To provide socio-economic infrastructure and ensure periodic review of plans & programmes for the construction and general maintenance of all public properties and drains |  |  |  |  |  |  |  |  |
| Sub Programme Objective: To facilitate the implementation of such polices in relation to physical planning, land use and development within the framework of national polices. |  |  |  |  |  |  |  |  |
| Physical and Spatial Planning Development | Outcome 1: Land use and development well managed |  |  |  |  |  |  |  |
|  | Output 1.1 | Base Maps and local plans prepared | No. of communities with base maps | 0 | 1 | 4 | 3 |  |
|  |  |  | No. of communities with local plans | 0 | 1 | 2 | 1 |  |
|  | Output 1.2 | Street Named and Property Addressed | No. of streets named | 0 | 5 | 9 | 4 |  |
|  |  |  | No. of properties addressed | 579 | 1000 | 0 | (1000) |  |
|  | Output 1.3 | Statutory planning committee meeting organized | No. of statutory planning committee meetings organized | 12 | 12 | 9 | (3) |  |
|  | Output 1.4 | Communities sensitised on development control | No. of public fora organized | 1 | 3 | 1 | (2) |  |
| Sub Programme Objective: To facilitate the implementation of such polices in relation to feeder roads, water and sanitation, rural housing and public works within the framework of national polices. |  |  |  |  |  |  |  |  |
| Public Works, Rural Housing and Water Management | Outcome 2: Access to basic infrastructure improved |  |  |  |  |  |  |  |
|  | Output 2.1 | Projects inspected | No. of site meetings organized | 11 | 20 | 6 | (14) |  |
|  | Output 2.2 | Electricity coverage improved | No. of communities connected to the National Grid | 10 | 12 | 3 | (9) |  |
|  | Output 2.3 | Portable water coverage improved | No. of boreholes constructed | 10 | 20 | 0 | (20) |  |
|  |  |  | No. of boreholes rehabilitated | 15 | 20 | 2 | (18) |  |
|  |  |  | No. of borehole mechanized | 12 | 1 | 0 | (1) |  |
|  | Output 2.4 | WSMTs formed and trained | No. of WSMTs formed and trained | 10 | 30 | 0 | (30) |  |
| Sub Programme Objective: To ensure quality and adequate provision of infrastructure such as roads, water, electricity whiles maintaining the existing ones. |  |  |  |  |  |  |  |  |
| Roads and Transport Services | Outcome 2: Road network improved |  |  |  |  |  |  |  |
|  | Output 3.1 | Reduced incidents of road accidents | No. of cases of accidents | 4 | 0 | 2 | (2) |  |
|  | Output 3.2 | Effective and efficient transport system provided | Kilometers of road cleared and opened up | 23 | 15 | 14.5 | (0.5) |  |
|  |  |  | Kilometers of roads reshaped | 15 | 11.5 | 9.8 | (1.7) |  |
|  |  |  | Kilometers of road rehabilitated | 2 | 11.5 | 1.7 | (9.8) |  |
|  |  |  | No. of culverts constructed on some existing roads | 0 | 5 | 0 | (5) |  |

Budget Programme Title: Economic Development

| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator |  | Baseline (2021) Actuals | 2022 |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Budget Year Target | Annual Actual | Variance |  |
| National Objective: Increase number of youth and adults with relevant skills |  |  |  |  |  |  |  |  |  |
| Programme Objective: To promote wealth, employment and food security through modernized agriculture, industry and growth of small-scale community-based enterprises. |  |  |  |  |  |  |  |  |  |
| Sub Programme Objective: - Expand opportunities for job creation and improve efficiency and competitiveness of Micro, Small and Medium Enterprises. - To improve private sector productivity and competitiveness; and - To provide the building of capital through progressive savings |  |  |  |  |  |  |  |  |  |
| Trade, Tourism and Industrial Development | Outcome 1: Opportunities for job creation expanded |  |  |  |  |  |  |  |  |
|  | Output 1.1 | Savings among rural folks enhanced | Number of women groups engaged in VSLA |  | 6 | 10 | 12 | 2 |  |
|  | Output 1.2 | Capacity of women in income generation ventures improved | No. of women groups equipped with simple business skills and bookkeeping |  | 6 | 10 | 15 | 5 |  |
|  | Output 1.3 | Potential and existing entrepreneurs counselled | No. of potential and existing entrepreneurs counselled |  | 155 | 100 | 94 | (6) |  |
|  | Output 1.4 | Potential and existing entrepreneurs trained | No. of individuals trained on boutique tie and dye making |  | 5 | 5 | 8 | 3 |  |
|  |  |  | No. of individuals trained on soup making |  | 25 | 25 | 31 | 6 |  |
|  | Output 1.5 | Access to credit by MSMEs facilitated | No. of new businesses established |  | 16 | 16 | 9 | (7) |  |
|  |  |  | No. of MSMEs who had access to credit |  | 15 | 15 | 12 | (3) |  |
| Sub Programme Objective: - To provide requisite skills and knowledge on agricultural technologies to farmers - To increase livestock production and enhance food security - To improve crop production and enhance food security |  |  |  |  |  |  |  |  |  |
| Agricultural Services and Management | Outcome 2: Food security improved |  |  |  |  |  |  |  |  |
|  | Output 2.1 | Capacity of women in income generation ventures improved | Number of women groups equipped with simple business skills and bookkeeping |  | 24 | 80 | 70 | (10) |  |
|  | Output 2.2 | Increase capacity of AEAs | No. of trainings for AEAs |  | 6 | 10 | 8 | (2) |  |
|  | Output 2.3 | New agronomical practices promoted | No. of household trained on good farming practices including | Land preparation | 35,456 | 40,000 | 36,569 | (3,431) |  |
|  |  |  |  | Improved farming technologies | 18,456 | 25,000 | 21,645 | (3,355) |  |
|  |  |  |  | Storage | 17,556 | 25,000 | - | (25,000) |  |
|  |  |  |  | Postharvest lost | 17,789 | 25,000 | - | (25,000) |  |
|  |  |  | No. of trainings for farmers on improved farming technologies |  | 15 | 20 | 17 | (3) |  |

Budget Programme Title: Environmental Management

| Sub-Programme | Type of Indicator | Description of Indicator | Unit of Measure of Indicator | Baseline (2021) Actuals | Year 2022 |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Budget Year Target | Annual Actual | Variance |  |
| National Objective: Reduce vulnerability to climate-related events and disasters |  |  |  |  |  |  |  |  |
| Programme Objective: - To ensure that ecosystem services are protected and maintained for future human generations. - To manage disasters by coordinating resources and developing the capacity of communities to respond effectively to disasters and improve their livelihood through social mobilization, employment generation and poverty reduction projects. |  |  |  |  |  |  |  |  |
| Sub Programme Objective: To plan and implement programmes to prevent and/or mitigate disaster in the Municipality within the framework of national policies. |  |  |  |  |  |  |  |  |
| Disaster Prevention and Management | Outcome 1: Disaster prevented and/or mitigated |  |  |  |  |  |  |  |
|  | Output 1.1 | Disaster victims supported | No. of victims supplied with relief items | 30 | 60 | 0 | (60) |  |
|  | Output 1.2 | Disaster volunteers trained | No. of volunteers trained | 2 | 25 | 0 | (25) |  |
|  | Output 1.3 | Campaigns on disaster prevention organized | No. of campaigns organized | 2 | 5 | 0 | (5) |  |
|  | Output 1.4 | Capacity of disaster managers built | No. of rapid response unit for disaster established | 1 | 2 | 0 | (2) |  |
|  |  |  | No. of bush fire volunteers trained | 17 | 50 | 22 | (28) |  |
| Sub Programme Objective: - To ensure that the ecosystem services are protected and maintained for future human generations. - To implement existing laws and regulations and programmes on natural resources utilisation and environmental protection. - Increase environmental protection through re-afforestation. |  |  |  |  |  |  |  |  |
| Natural Resources Conservation and Management | Outcome 2: Increased environmental protection |  |  |  |  |  |  |  |
|  | Output 2.1 | Trees planted | Number of seedlings developed and distributed | 80000 | 100000 | 0 | (100000) |  |

# PART D: KEY FINANCIAL PERFORMANCE BY PROGRAMME FOR THE PERIOD

| Financial |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | Budget Programme/ Sub-Programme Name | Approved Budget (2022) | Total Approved Budget By Fund Source |  |  |  |  |  | Budget (All Funding Sources) 2022 | Actual Expenditure For 2022 | Actual Payments For 2022 | Projections For 2023 |
|  |  |  | GOG | DACF-RFG | IGF | SCH4G | MAG | DACF |  |  |  |  |
| P1 | Management and Administration |  |  |  |  |  |  |  |  |  |  |  |
| SP1.1 | General Administration | 2,156,524.84 | 842,513.58 | 0.00 | 170,180.00 | 0.00 | 0.00 | 1,431,832.26 | 2,156,524.84 | 3,889,122.22 | 3,396,881.39 | 4,800.00 |
| SP1.2 | Finance and Audit | 185,225.78 | 98,225.78 | 0.00 | 49,000.00 | 0.00 | 0.00 | 38,000.00 | 185,225.78 | 165,789.00 | 165,789.00 | 1,689,085.21 |
| SP1.3 | Human Resource Development | 120,926.54 | 45,267.54 | 45,859.00 | 4,000.00 | 0.00 | 0.00 | 25,800.00 | 120,926.54 | 94,356.29 | 94,356.29 | 195,684.06 |
| SP1.4 | Planning, Budgeting, Monitoring & Evaluation and Statistics | 452,472.49 | 281,472.49 | 0.00 | 8,000.00 | 0.00 | 0.00 | 163,000.00 | 452,472.49 | 432,051.68 | 432,051.68 | 180,226.54 |
| SP1.5 | Legislative Oversight | 46,000.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 46,000.00 | 46,000.00 | 43,800.00 | 43,800.00 | 562,062.49 |
| P2 | Total Programme 1 | 2,961,149.65 | 1,267,479.39 | 45,859.00 | 231,180.00 | 0.00 | 0.00 | 1,704,632.26 | 2,961,149.65 | 4,625,119.88 | 4,132,878.36 | 2,631,858.30 |
| P2 | Social Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| SP2.1 | Education, Youth and Sports Services | 2,038,115.06 | 0.00 | 803,416.31 | 21,320.00 |  |  | 1,213,379.00 | 2,038,115.06 | 958,382.25 | 835,751.24 | 1,667,778.15 |
| SP2.2 | Public Health Services and Management | 1,841,175.74 | 0.00 | 450,000.00 | 5,000.00 | 490,000.00 |  | 896,175.74 | 1,841,175.74 | 533,930.00 | 533,930.00 | 2,467,453.52 |
| SP2.3 | Environmental Health and Sanitation Services | 1,583,597.46 | 437,386.46 | 33,000.00 | 15,000.00 | 830.019.00 | 0.00 | 268,192.00 | 1,583,597.46 | 992,619.96 | 992,619.96 | 1,134,021.76 |
| SP2.5 | Social Welfare and Community Development | 1,361,923.68 | 226,903.68 | 0.00 | 16,800.00 | 0.00 | 0.00 | 1,118,220.00 | 1,361,923.68 | 520,341.95 | 520,341.95 | 987,928.25 |
|  | Total Programme 2 | 4,786,696.88 | 664,290.14 | 1,286,416.31 | 58,120.00 | 1,320,019.00 | 0.00 | 3,495,966.74 | 4,786,696.88 | 3,005,274.16 | 2,882,643.15 | 6,257,181.68 |
| P3 | Infrastructure Delivery and Management |  |  |  |  |  |  |  |  |  |  |  |
| SP3.1 | Roads and Transport Services | 370,000.00 | 0.00 | 250,000.00 | 0.00 | 0.00 | 0.00 | 120,000.00 | 370,000.00 | 170,140.25 | 170,140.25 | 42,322.00 |
| SP3.2 | Physical and Spatial Planning Development | 227,625.80 | 0.00 | 0.00 | 2,000.00 | 0.00 | 0.00 | 105,625.80 | 227,625.80 | 227,625.80 | 0.00 | 281,451.68 |
| SP3.3 | Public Works, Rural Housing and Water Management | 1,532,920.16 | 76,810.16 | 0.00 | 39,822.00 | 0.00 | 0.00 | 1,166,338.00 | 1,532,920.16 | 333,388.41 | 333,388.41 | 1,798,083.56 |
|  | Total Programme 3 | 1,760,545.96 | 76,810.16 | 250,000.00 | 41,822.00 | 0.00 | 0.00 | 1,391,963.80 | 2,130,545.96 | 731,154.46 | 503,528.66 | 2,121,857.24 |
| P4 | Economic Development |  |  |  |  |  |  |  |  |  |  |  |
| SP4.1 | Agricultural services and management | 832,115.26 | 597,106.40 | 0.00 | 13,500.00 | 0.00 | 96,508.86 | 125,000.00 | 832,115.26 | 832,115.26 | 549,593.06 | 1,287,949.43 |
| SP4.2 | Trade, tourism and industrial management | 226,500.00 | 0.00 | 85,000.00 | 76,500.00 | 0.00 | 0.00 | 65,000.00 | 226,500.00 | 0.00 | 0.00 | 140,600.00 |
|  | Total Programme 4 | 1,058,615.26 | 597,106.40 | 85,000.00 | 90,000.00 | 0.00 | 96,508.86 | 190,000.00 | 1,058,615.26 | 832,115.26 | 549,593.06 | 1,428,549.43 |
| P5 | Environmental Management |  |  |  |  |  |  |  |  |  |  |  |
| SP5.1 | Disaster prevention and management | 45,000.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 45,000.00 | 45,000.00 | 0.00 | 0.00 | 28,878.52 |
| SP5.2 | Natural Resource Conservation and management | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | Total Programme 5 | 45,000.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 45,000.00 | 45,000.00 | 0.00 | 0.00 | 28,878.52 |
|  | Grand Total | 12,604,172.81 | 2,605,686.09 | 1,667,275.31 | 421,122.00 | 1,320,019.00 | 96,508.86 | 6,493,561.55 | 12,604,172.81 | 8,361,547.81 | 8,109,457.84 | 12,468,325.17 |

# PART E: SUMMARY OF EXPENDITURE BY ECONOMIC CLASSIFICATION

| Expenditure Item | Approved Budget (2022) | Amount for 2022 | Actual Expenditure for the Period Ending 31st December 2022 | Actual Payments for the Period Ending 31st December 2022 | Projections for Next Period Ending 31st December 2023 |
| --- | --- | --- | --- | --- | --- |
| Compensation of Employees | 2,557,922.00 | 2,557,922.00 | 3,583,978.31 | 3,583,978.31 | 2,720,405.00 |
| Goods and Services | 5,875,926.90 | 5,875,926.90 | 2,648,181.18 | 2,648,181.18 | 4,906,681.00 |
| Capital Expenditure | 4,170,325.00 | 4,170,325.00 | 1,877,298.35 | 1,877,298.35 | 4,841,239.17 |
| Total | 12,604,173.90 | 12,604,173.90 | 8,109,457.84 | 8,109,457.84 | 12,468,325.17 |

# PART F: CASH POSITION

| Accounts | Account Balances as at 31st December, 2022 |
| --- | --- |
| Sub CF |  |
| GoG | 20,099.61 |
| DACF-RFG | 44,015.63 |
| DACF – Assembly | 13,579.55 |
| DACF - MP | 404,176.10 |
| DACF - PWD | 107,858,36 |
| M-SHAP | 3,747.10 |
| Sanitation Challenge for Ghana (SCH4G) | 10,944.64 |
| Modernizing Agriculture in Ghana (MAG) | 0.00 |
| IGF | 32,637.65 |
| Total Cash position | 529,200.28 |

Revenue Projection – All Revenue Sources

| Items | 2020 |  | 2021 |  | 2022 |  | % as at December |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Budget | Actuals | Budget | Actuals | Budget | Actuals as at December |  |
| IGF | 450,115.00 | 413,634.39 | 363,849.10 | 445,661.91 | 420,122.00 | 423,594.85 | 100.83 |
| Compensation Transfer | 1,793,162.26 | 1,209,788.00 | 2,077,583.09 | 2,334,996.87 | 2,429,753.39 | 3,494,173.31 | 143.81 |
| Goods and Services Transfer | 70,047.83 | 54,951.82 | 77,230.00 | 54,753.51 | 93,263.00 | 29,440.37 | 31.57 |
| Assets Transfer | 0.00 | 0.00 | 0.00 | 0 | 25,180.00 | 0.00 | 0.00 |
| DACF – Assembly | 4,994,662.74 | 2,460,502.29 | 3,276,687.61 | 896,743.85 | 5,517,706.91 | 2,066,416.26 | 40.06 |
| DACF – PWD | 307,500.00 | 506,412.27 | 307,500.00 | 100,133.25 | 307,500.00 | 110,086.49 | 35.80 |
| DACF – MP | 342,076.00 | 201,224.17 | 342,076.00 | 294,652.07 | 703,845.43 | 460,077.15 | 65.37 |
| M-SHAP | 19,725.74 | 9,054.28 | 19,725.74 | 2,330.09 | 20,000.00 | 19,725.74 | 98.62 |
| DACF-RFG | 2,710,679.38 | 797,344.81 | 771,315.00 | 1,133,812.00 | 1,667,275.31 | 1,162,183.92 | 69.25 |
| MAG | 251,843.00 | 176,290.10 | 118,887.00 | 48,850.00 | 96,508.86 | 27,573.96 | 28.57 |
| SCH4G | 2,068,033.00 | 1,905,929.72 | 1,291,500.00 | 0.00 | 1,323,019.00 | 0.00 | 0.00 |
| CW-GIZ |  |  | 48,850.00 | 79,052.28 | 0.00 | 0.00 | 0.00 |
| Total | 13,007,844.95 | 7,735,131.85 | 8,695,203.54 | 5,390,985.83 | 12,604,173.90 | 7,793,972.36 | 61,84 |

# PART G (i): SUMMARY OF 2022 IGF PERFORMANCE BY REVENUE ITEMS FOR THE PERIOD

| Revenue Categories | Projections/ Budget | Actual Collection Period Ending 31st December 2022 | Payment into Assembly Account Period Ending 31st December 2022 | Remarks |
| --- | --- | --- | --- | --- |
| Property Rate | 8,002.00 | 32,516.35 | 32,516.35 |  |
| Other Rates | 33,501.60 | 7,100.00 | 7,100.00 |  |
| Fees | 132,224.40 | 178,541.15 | 178,541.15 |  |
| Fines | 8,820.00 | 0.00 | 0.00 | No fine was collected |
| Licenses | 66,948.45 | 73,281.00 | 73,281.00 |  |
| Land | 35,023.00 | 0.00 | 0.00 |  |
| Rent | 126,569.95 | 125,640.00 | 125,640.00 |  |
| Investment | 9,032.60 | 6,516.35 | 6,516.35 |  |
| Total | 420,122.00 | 423,594.85 | 423,594.85 |  |

## (II): EXPENDITURES ON 2022 IGFS BY ECONOMIC CLASSIFICATION

| Expenditure Item | Approved Budget | Actual Expenditure for the Period January to December, 2022 |
| --- | --- | --- |
| Compensation of Employees | 190,055.00 | 89,805.00 |
| Goods and Services | 274,079.40 | 301,152.20 |
| Capital Expenditure | 85,000.00 | 0.00 |
| Totals | 420,122.40 | 390,957.20 |

# PART H: STAFF ESTABLISHMENT BY GRADE (GOG ONLY)

| S/N | Grade | No. at post as at 31st December 2021 | No. at post as at 31st December 2022 | Projections for 2023 | Projections for 2024 | Projections for 2025 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Agricultural Officer (AO) | 1 | 1 | 1 | 1 | 1 |
|  | Animal Health Officer (AHO) | 1 | 1 | 1 | 1 | 1 |
|  | Animal Production Officer | 1 | 1 | 1 | 1 | 1 |
|  | Animal Production Officer (APO) | 1 | 1 | 1 | 1 | 1 |
|  | Assistant Agricultural Officer (AAO) | 2 | 2 | 2 | 2 | 2 |
|  | Assistant Budget Analyst | 5 | 5 | 5 | 5 | 5 |
|  | Assistant Budget Officer | 0 | 1 | 1 | 1 | 1 |
|  | Assistant Catering Officer | 1 | 1 | 1 | 1 | 1 |
|  | Assistant Development Planning Officer | 1 | 1 | 1 | 1 | 1 |
|  | Assistant Director I | 1 | 1 | 1 | 1 | 1 |
|  | Assistant Director IIB | 4 | 6 | 6 | 6 | 6 |
|  | Assistant Engineer | 2 | 2 | 2 | 2 | 2 |
|  | Assistant Human Resource Manager | 0 | 2 | 2 | 2 | 2 |
|  | Assistant Internal Audit (Trainee) | 0 | 1 | 1 | 1 | 1 |
|  | Assistant Internal Auditor | 2 | 2 | 2 | 2 | 2 |
|  | Assistant Physical Planner | 0 | 1 | 1 | 1 | 1 |
|  | Assistant Procurement Officer | 1 | 1 | 1 | 1 | 1 |
|  | Assistant Programmer | 0 | 1 | 1 | 1 | 1 |
|  | Assistant Security Officer | 0 | 1 | 1 | 1 | 1 |
|  | Assistant Statistician | 1 | 1 | 1 | 1 | 1 |
|  | "Asst. Chief Tech. Officer | 1 | 1 | 1 | 1 | 1 |
|  | Chief Environmental Health Assistant | 8 | 8 | 8 | 8 | 8 |
|  | Chief Technical Officer (C.T.O) | 2 | 2 | 2 | 2 | 2 |
|  | Deputy Director | 1 | 1 | 1 | 1 | 1 |
|  | District Coordinating Director | 1 | 1 | 1 | 1 | 1 |
|  | Driver GD II | 1 | 1 | 1 | 1 | 1 |
|  | Driver GD III | 1 | 1 | 1 | 1 | 1 |
|  | Driver III | 1 | 1 | 1 | 1 | 1 |
|  | Environmental Health Assistant | 14 | 14 | 14 | 14 | 14 |
|  | Foreman | 1 | 1 | 1 | 1 | 1 |
|  | Headman Labourer | 8 | 8 | 8 | 8 | 8 |
|  | Headman Watchman | 1 | 1 | 1 | 1 | 1 |
|  | Health Overseer | 1 | 1 | 1 | 1 | 1 |
|  | Heavy Duty Driver | 1 | 1 | 1 | 1 | 1 |
|  | Higher Revenue Inspector | 1 | 1 | 1 | 1 | 1 |
|  | Junior Foreman | 1 | 1 | 1 | 1 | 1 |
|  | Labourer | 2 | 2 | 2 | 2 | 2 |
|  | Mass Education Officer | 2 | 2 | 2 | 2 | 2 |
|  | Principal Development Planning Officer | 1 | 1 | 1 | 1 | 1 |
|  | Principal Environmental Health Assistant | 6 | 6 | 6 | 6 | 6 |
|  | Principal Internal Auditor | 1 | 1 | 1 | 1 | 1 |
|  | Principal Radio Operator | 1 | 1 | 1 | 1 | 1 |
|  | Principal Social Development Officer | 1 | 1 | 1 | 1 | 1 |
|  | Principal Technical Officer (PTO) | 1 | 1 | 1 | 1 | 1 |
|  | Senior Agricultural Officer (SAO) | 2 | 2 | 2 | 2 | 2 |
|  | Senior Animal Production Officer (SPO) | 2 | 2 | 2 | 2 | 2 |
|  | Senior Budget Analyst | 1 | 1 | 1 | 1 | 1 |
|  | Senior Development Planning Officer | 2 | 2 | 2 | 2 | 2 |
|  | Senior Environmental Health Assistant | 8 | 8 | 8 | 8 | 8 |
|  | Senior Executive Officer | 3 | 4 | 4 | 4 | 4 |
|  | Senior Human Resource Manager | 1 | 1 | 1 | 1 | 1 |
|  | Senior Internal Auditor | 1 | 1 | 1 | 1 | 1 |
|  | Senior Mass Education Officer | 1 | 1 | 1 | 1 | 1 |
|  | Senior Records Supervisor | 1 | 1 | 1 | 1 | 1 |
|  | Senior Social Development Officer | 3 | 3 | 3 | 3 | 3 |
|  | Stenographer GD II | 2 | 2 | 2 | 2 | 2 |
|  | Technical Officer (T.O) II | 2 | 2 | 2 | 2 | 2 |
|  | Technical Assistant | 1 | 1 | 1 | 1 | 1 |
|  | Technical Officer (TO) II | 7 | 7 | 7 | 7 | 7 |
|  | Tractor Operator | 1 | 1 | 1 | 1 | 1 |
|  | Typist II | 1 | 1 | 1 | 1 | 1 |
|  | Watchman | 1 | 1 | 1 | 1 | 1 |
|  | Watchman (Day) | 2 | 2 | 2 | 2 | 2 |
|  | Yard Foreman | 2 | 2 | 2 | 2 | 2 |
|  | Total | 127 | 137 | 137 | 137 | 137 |

# PART I: IGF STAFF BY NON-ESTABLISHED POST

| S/N | Grade | No. at post as at 31st December 2021 | No. at post as at 31st 2022 | Projections for 2023 | Projections for 2024 | Projections for 2025 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Cemetery Guard | 1 | 1 | 1 | 1 | 1 |
| 2 | Cleaner | 11 | 11 | 11 | 11 | 11 |
| 3 | Day Watchman | 1 | 2 | 3 | 3 | 3 |
| 4 | Driver | 1 | 1 | 1 | 1 | 1 |
| 5 | Driver Mate | 1 | 1 | 1 | 1 | 1 |
| 6 | Electrician | 1 | 1 | 1 | 1 | 1 |
| 7 | Labourer | 6 | 6 | 6 | 6 | 6 |
| 8 | Night Watchman | 5 | 5 | 6 | 6 | 6 |
| 9 | RDA | 1 | 1 | 1 | 1 | 1 |
| 10 | Receptionist | 1 | 1 | 0 | 0 | 0 |
| 11 | Resource Assistant | 0 | 2 | 2 | 2 | 2 |
| 12 | Sanitation Labourer | 1 | 1 | 1 | 2 | 2 |
|  | TOTAL | 30 | 33 | 34 | 35 | 35 |

# PART J: ACTIONS TAKEN TO IMPLEMENT THE RECOMMENDATIONS OF PARLIAMENT IN RESPECT OF THE MOST RECENT REPORT OF THE AUDITOR-GENERAL IN ACCORDANCE WITH SECTION 27(4)(d) OF PFM Act

| S/N | Recommendations By Parliament | Actions Taken | Remarks |
| --- | --- | --- | --- |
| 1 | No recommendation was made by PAC |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |

# PART K: DETAILS OF ON-GOING PROJECTS

| S/N | Name of Project and Location (a) | Contract Sum (b) | Variations in Contract sum | Total Revised Contract Sum (c) | Actual Payments to date | Balance | Last Payment made |  | Amount Budgeted for 2022 | Amount programmed for 2023 | Amount programmed for 2024 | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Date | Amount |  |  |  |  |
| 1 | Construction of 1 No. 3-Unit at Kasapoe | 380,037.10 | 0.00 | - | 180,518.00 | 199,519.10 | 29/12/2022 | 62,328.49 | 380,037.10 | 137,190.61 | 0.00 | Roofing level |
| 2 | Construction of 1 No. 3-Unit with at Afayili | 245,335.74 | 0.00 | - | 233,06895 | 12,266.79 | 29/12/2022 | 24,524.70 | 245,335.74 | 12,266.79 | 0.00 | Completed and in use |
| 3 | Construction of 1 No. 3-Unit Classroom Block with 4-Unit KVIP, 2-Unit Urinal, and Supply of 75 No. Steel Dual Desk & 4 No. Teachers Tables at Gambuga | 111,055.45 | 0.00 | - | 87,749.12 | 23,306.33 | 14/11/2022 | 18,255.25 | 111,055.45 | 23,306.33 | 0.00 | Completed and in use |
| 4 | Rehabilitation and Furnishing 1 No. 3-Unit Classroom Block at Dakpam | 237,300.60 | 0.00 | - | 225,435.00 | 11,865.00 | 14/11/2022 | 101,006.04 | 237,300.60 | 11,865.00 | 0.00 | Completed and in use |
| 5 | CHPs Compound at Jakpumba | 200,102.00 | 0.00 | - | 190,096.90 | 10,005.10 | 06/10/2022 | 17,101.00 | 200,102.00 | 10,005.10 | 0.00 | Completed and in use |
| 6 | CHPs Compound at Kanjonaya | 285,200.00 | 0.00 | - | 270,940.00 | 14.260.00 | 03/11/2022 | 101,840.00 | 285,200.00 | 14.260.00 | 0.00 | Completed and in use |
| 7 | Rehabilitation of 1 No. 5-Unit Pavilion at Kasimiyya and 1 No. 3-Unit Classroom Block at Ponaa Girls Model | 250,004.50 | 0.00 | - | 0.00 | 250,004.50 | - | 0.00 | 250,004.50 | 250,004.50 | 0.00 | Site handed over to contractor |

# PART L: CONCLUSION

Education, health and agriculture continue to remain the focus of the Municipal Assembly. Chunk of the Assembly’s resource is channeled into provision of education and health infrastructure and delivery agricultural extension towards the achievement of SDG 2, 3 and 4. The Assembly has more plans in place towards the achievement of quality education, good health and well-being, zero hunger, and no poverty. Revenue improvement strategies have been set to increase internal generated fund to improve development in the municipality.